## Tasks
Upgrade Netweaver 2004s
Nr. | Area | Activity | System | Description | Duration | Start | End | Responsible | Status
| BASIS |  | Sandbox | copy one Production System to a Sandbox System
| BASIS |  | Sandbox | establish RFC Connections btw Source Systems and Sandbox
| BASIS |  | Sandbox | Acquisition of new Hardware (e.g. for BI Accelerator)
| BASIS |  | Sandbox | Identification and Communication of necessary System Reqirements (SAP Kernel, Storage, PI, Stacks)
| BASIS |  | Sandbox | Definition of additional technical Infrastructure Requirements (e.g. EP, BW GUI, SAP GUI,J2EE, MS Office)
| APPLI | Activity | Sandbox | Upgrade Preparation (Applicationside) - e.g. Check OSS Notes, Definition of Test Cases/Test Scripts
| APPLI | Task | Sandbox | check the Status of your Information Objects before the Upgrade and repair them if necessary (see Note 458363)
| APPLI | Task | Sandbox | check MD Consistency in Transaction SE38
| APPLI | Task | Sandbox | run Report RSUPGRCHECK
| APPLI | Task | Sandbox | check that M Tables are empty (ODS Tables)
| APPLI | Task | Sandbox | release Transport Requests and Repairs
| APPLI | Task | Sandbox | check with SE14 for Mass Activation in Transaction SE14
| APPLI | Task | Sandbox | check for Deletion of Jobs with Report RSBTCDEL2 in Transaction SE14 (see Note 784969)
| APPLI | Task | Sandbox | check with RSCPINST the right Codepage Settings in Trasaction SE38
| BASIS | Activity | Sandbox | Upgrade Preparation (BASIS) prepare Upgrade ABAP Stack (incl. DB Upgrade)
| BASIS | Task | Sandbox | use the latest Version of tp, R3trans, R3load and SPAM/SAINT on the Start (4.x, 6.x) and Target Release (7.00)
| BASIS | Task | Sandbox | check the latest SAPup in the Directory /usr/sap/put/bin (UNIX) and /usr/sap/put/exe (W2K)
| BASIS | Task | Sandbox | check the Tools tp, R3trans, dboraslib in the Directory /usr/sap/put/tools
| BASIS | Task | Sandbox | check the Upgrade Tools for Basis 7.00
| BASIS | Task | Sandbox | check Pre Requisites on Windows (see Note 816211)
| BASIS | Task | Sandbox | start PREPARE on Windows
| BASIS | Task | Sandbox | start the UaServer on Windows
| BASIS | Task | Sandbox | use Upgrade Assistent
| BASIS | Task | Sourcesystem | select PI in Phase IS_SELECT (see Note 86985)
| BASIS | Task | Sandbox | check the File System and r-w Permission
| BASIS | Task | Sandbox | run additional Scripts located in /usr/sap/put/bin copy the *sql Scripts located in /usr/sap/put/bin to $ORACLE_HOME/dbs
| BASIS | Task | Sandbox | define the Entrys for the Shadow Instance in /etc/services
| BASIS | Task | Sandbox | Error Handling
| BASIS | Task
| BASIS | Task | Sandbox | check and Import latest SPAM Update BEFORE you upgrade (Note 886784)
| BASIS | Task | Sandbox | cleaning up Table TBATG (SE14) e.g. Match Codes or Conversion Entrys (tp getprots <SAPSID>)
| BASIS | Task | Sandbox | cleaning up of Updates and RFC Calls
| BASIS | Task | Sandbox | check the Write Permission for the File /usr/sap/<SID>/SYS/exe/run/saposcol and the DBATOOLS
| BASIS | Task | Sandbox | check unused Job Logs with Report RSBTCDEL2 and clean out if possible
| BASIS | Task | Sandbox | check with the Program RSCPINST the right Codepage Settings
| BASIS |  |  | if there are Inconsistencys during the PREPARE Phase CNV_LIST, please run the Scripts Catalog.sql and catproc.sql to synchronize the DB with the SAP DDIC
| BASIS | Task | Sandbox | check all Login/* Parameters in the Default and Instance Profile
| BASIS | Task | Sandbox | make sure that you implement the automatic undo Management (AUM). see Note 600141 for Details
| BASIS | Task | Sandbox | provide enough Space in the File System (if you have not already created a locally managed temporary Table Space (PSAPTEMP2)).
| BASIS | Activity | Sandbox | Technical Upgrade
| BASIS | Task | Sandbox | upgrade Sandbox to NetWeaver 2004s and SEM 6.0 (ABAP Stack)
| BASIS | Task | Sandbox | Installation Add-in BI JAVA , Implement SP Stack SP 8 or SP 9
| BASIS | Task | Sandbox | Configuration and Checks of BI JAVA
| BASIS | Task | Sandbox | upgrade NW04s BW Frontend and SAP GUI
| BASIS | Activity | Sandbox | Post-Upgrade Activitys (BASIS)
| BASIS | Task | Sandbox | check the LONGPOST.LOG File for Conversion Errors
| BASIS | Task | Sandbox | run the BTCTRNS2 Program with User DDIC in Client 000 to restart Jobs
| BASIS | Task | Sandbox | run Transaction SGEN create ABAP Loads (Report Generation)
| BASIS | Task | Sandbox | run ./saproot.sh <SID> with user root
| BASIS | Task | Sandbox | run sapdba_role Script (on Oracle)
| BASIS | Task | Sandbox | check the Database Mode
| BASIS | Task | Sandbox | create Database Statistics
| BASIS | Task | Sandbox | distribute the new Kernel (unless done already)
| BASIS | Task | Sandbox | set the SAP BI Menu with Transaction SSM2
| BASIS | Task | Sandbox | RS00 for SAP BI
| BASIS | Task | Sandbox | UG00 for SEM
| BASIS | Task | Sandbox | apply the latest SPAM/SAINT Update (during Go-live Stage of the System)
| BASIS | Task | Sandbox | check the additional Notes for Correction for your Support Package Level of SAP NW04s, use Transaction SNOTE to implement the Correction (Example with SAP NW04s Patches)
| BASIS | Task | Sandbox | activate the Source Systems again (see Note 538052 for Details)
| BASIS | Task | Sandbox | run Transaction RSD1 --> repair Info Objects.
| BASIS | Task | Sandbox | run SE38 --> RS_TRANSTRU_ACTIVATE_ALL to activate all Transfer Structures again
| BASIS | Task | Sandbox | check Note 563201 in advance and use SAP_FACTVIEWS_RECREATE to create dropped Fact Views again
| BASIS | Task | Sandbox | check Note 634458 to avoid ODS Activation Errors (DEADLOCK)
| BASIS | Task | Sandbox | run Rransaction RSMDCNVEXIT again to avoid Errors with the following Support Packages see Notes 519791 (Windows) or 519654 (Unix)
| BASIS | Task | Sandbox | run Function Module RSOD_BUILD_ROOT_FOLDERS to avoid Problems with the BEx Download Scheduler, see Note 499480 for Details
| APPLI | Task | Sandbox | fill the Repository Cache for delivered Objects (from 3.0B Patch 10 Onwards) in Transaction RSORBCT
| APPLI | Task | Sandbox | activate the BEx History with Transaction RS_PERS_ACTIVATE
| APPLI | Task | Sandbox | run Report RSAPO_CLOSE_TRANS_REQUEST_ALL3, see Note 568441 for more Details (SEM-related)
| APPLI | Task | Sandbox | check if you have Problems when changing Key Figures on fixed Currency/Unit using Report RSDG_CUBE_TABLES_CONVERT. use Transaction RSD2 to repair the Inconsistency which only occurs at DDIC Level, see Note 616361
| APPLI | Task | Sandbox | check Note 585606 and use Transaction RSDMPRO to create missing TADIR Entrys for Multi Providers created in Release 2.x
| APPLI | Task | Sandbox | check Note 540720 for the new Authorization Object which is also needed with SAP BI Release 7.00 (S_RS_COMP1)
| BASIS | Task | Sandbox | run Report RS_DME_PGM_TADIR_CREATE_ENTRY if you have not run it prior to starting PREPARE
| BASIS | Task | Sandbox | check Note 642989 with BC_320 or higher
| BASIS | Task | Sandbox | reactivate the SAP BI System after Upgrade
| BASIS | Task | Sandbox | Basis, Application Support Packages, Stack
| BASIS | Task | Sourcesystem | check of SP for Plug-in for Source System (e.g. PI2004.1)
| BASIS | Task | Sandbox | Testing of RFC Connections
| BASIS | Task | Sandbox | run the Upgrade Report rsupgsum in the ABAP Workbench
| BASIS | Task | Sandbox | execute SAP System Upgrade Evaluation
| APPLI | Activity | Sandbox | Post-Upgrade Activitys (Application)
| APPLI | Task | Sandbox | RUN Transaction SPAU
| APPLI | Task | Sandbox | RUN UCCHECK (for Unicode Migration)
| APPLI | Task | Sandbox | V3-Bookings should remain stopped
| APPLI | Task | Sandbox | last Load of Deltas (especially Logistics) to clear Delta Queues
| APPLI | Task | Sandbox | all DSOs must have Status "green"!
| APPLI | Task | Sandbox | check for latest OSS Notes to be implemented
| APPLI | Task | Sandbox | migrate Charts in Web Reports (review Notes 832712 and 844012!)
| APPLI | Task | Sandbox | Assignment of DataSources to InfoSources
| APPLI | Task | Sandbox | Testing of Extractors
| APPLI | Task | Sandbox | Definition of InfoPackages for Source System
| APPLI | Task | Sandbox | update Processchain for Source System
| APPLI | Task | Sandbox | Testing of Processchain (Loading of Transactional Data and Master Data)
| APPLI | Task | Sandbox | restart Loading Data of Core Processes (at least one Time)
| APPLI | Task | Sandbox | execute Reports of each Application Area as well as other Applications according to Test Cases
| APPLI | Task | Sandbox | switch from new NW04s Authorizations Concept to old RSSM Authorization Concept in TC SPRO
| APPLI | Task | Sandbox | fix Authorization Issues due to new Standard Authorization Objects in Backend (no Analysis Authorizations)
| APPLI | Task | Sandbox | run Transaction RSD1 to check InfoObjects and check Expert Settings in RSD1
| APPLI | Task | Sandbox | run Alpha Conversion again after Upgrade in Transaction RSMDCNVEXIT
| APPLI | Task | Sandbox | run Program SAP_FACTVIEWS_RECREATE in Transaction SE38, see Note 563201 for more Details
| APPLI | Task | Sandbox | run Function Module RSOD_BUILD_ROOT_FOLDERS in Transaction SE37
| APPLI | Task | Sandbox | check BW Documents, run Function Module SKWF_APPL_ROOT_IOS_GET in Transaction SE37, check Note 499480
| APPLI | Task | Sandbox | filling the Meta Data Repository Cache in Transaction RSA1
| APPLI | Task | Sandbox | activate BEx History (RS_PERS_ACTIVATE) in Transaction SPRO
| APPLI | Task | Sandbox | create missing TADIR Entrys for MultiProviders
| APPLI | Task | Sandbox | check RSADMINSV View and Content Settings
| APPLI | Task | Sandbox | check the correct Installation of the BI Frontend
| APPLI | Task | Sandbox | check the Document Attributes in RSA1
| BASIS | Task | Sandbox | maintain Values with SM30_SSM_VAR
| APPLI | Task | Sandbox | check Standard IMG with SPRO. Maintain SAP BI System Tables RSADMIN* via Standard IMG
| APPLI | Task | Sandbox | check the basic Customizing Settings in SPRO
| APPLI | Task | Sandbox | check global Settings in SAP NW04s (TC RSADMIN) -->RSCUSTA2 (Note 629987 and 554521)
| APPLI | Task | Sandbox | check basic Customizing Settings in RSCUSTV8 (Note 647002 and 653469) and RSRCACHE and RSCUSTV14 (Note 683194)
| APPLI | Task | Sandbox | check RSCUSTV15 and RSCUSTV16
| APPLI | Task | Sandbox | check new Performance Settings for NW04s in SPRO
| APPLI | Task | Sandbox | check new Maintenance of the Statistic Data Collection via RSDDSTAT
| APPLI | Activity | Sandbox | Post-Upgrade Activitys (Application - Web-specific)
| APPLI | Task | Sandbox | check Note 591990 and maintain the Values for the Reporting Agent , if you wish to use predefined Web Templates
| APPLI | Task | Sandbox | Check the BEx web settings
| APPLI | Task | Sandbox | run Report RSZW_WEBOBJECTS_30_UPGRADE to move the Web Objects to the new Repository
| APPLI | Task | Sandbox | run Report RSZW_OLD_BDS_ENTRIES_DELETE to clean the old BDS, see Notes 484390 and 484878
| BASIS | Task | Sandbox | install the IGS 7.00 according to Note 732502
| BASIS | Task | Sandbox | run Report RSZW_ITEM_MIGRATION_3X_TO_70 to start the Conversion of the existing Chart Settings from BMP to XML, see Note 832712 for more Details
| APPLI | Task | Sandbox | Testers must sign off the Test Scripts
| APPLI | Activity | Sandbox | functional Testing of new NW04s Functionalitys
| APPLI | Task | Sandbox | Testing of Test Querys with new NW04s Editors (WAD, Bex, Report Designer, Workbook Designer etc.)
| APPLI | Task | Sandbox | Testing for BI Accelerator
| APPLI | Task | Sandbox | Testing of Integrated Planning Functionality
| APPLI | Task | Sandbox | Testing of Information Broadcaster
| APPLI | Task | Sandbox | Monitoring Testing (AdminCockpit)
| APPLI | Task | Sandbox | Definition and Testing of Transformation Scenario
| APPLI | Activity | Sandbox | Lessons learned (to be applied for Development System Upgrade)
| APPLI | Activity | Sandbox | Migration of Authorization Objects
| APPLI | Task | Sandbox | run ABAP Program RSEC_MIGRATION in Transaction SA38
Note on B3: Monikla Klarl: SAP NetWeaver 7.0 oder 7.x?
Note on E7: Monikla Klarl: between?
Note on E8: Monikla Klarl: SAP NetWeaver BW Accelerator?
Note on E19: Monikla Klarl: Code Page?
Note on E21: Monikla Klarl: Diese Begriffe kann ich nicht prüfen.
Note on E22: Monikla Klarl: SAPup???
Note on E27: Monikla Klarl: UaServer?
Note on E29: Monikla Klarl: SAP NetWeaver PI?
Note on E43: Monikla Klarl: Undo Management?
Note on E46: Monikla Klarl: SAP NetWeaver 7.0 oder 7.x?
Note on E50: Monikla Klarl: post Upgrade Activitys oder Post Upgrade Activitys?
Note on E59: Monikla Klarl: SAP NetWeaver BW
Note on E60: Monikla Klarl: s.o.
Note on E63: Monikla Klarl: Bitte die Versionen prüfen.
Note on E76: Monikla Klarl: SAP NetWeaver BW 7.0?
Note on E79: Monikla Klarl: BW-System
Note on E85: Monikla Klarl: post Upgrade Activitys? Oder Post Upgrade Activitys?
Note on E86: Monikla Klarl: run
Note on E87: Monikla Klarl: run
Note on E90: Monikla Klarl: DSOs korrekt?
Note on E100: Monikla Klarl: Bitte die Versionen prüfen.
Note on E111: Monikla Klarl: SAP NetWEaver BW
Note on E114: Monikla Klarl: SAP NetWeaver BW
Note on E116: Monikla Klarl: Version prüfen.
Note on E119: Monikla Klarl: Bitte Version prüfen.
Note on E121: Monikla Klarl: Post Upgrade Activitys oder post Upgrade Activitys?
Note on E129: Monikla Klarl: Bitte die Version prüfen.
Note on E130: Monikla Klarl: Bitte Version prüfen.
Note on E131: Monikla Klarl: SAP NetWeaver BW Accelerator