## Effort Estimation (EN) Screensh
Company
[8 empty] | Data Analysis |  |  |  | Tools | Data Cleansing |  | Mapping | Implementation |  | Tests | [5 empty] | Productive Load |  | Data Validation |  | Column | Row
No. | Area | Migration Object english | Migrationsobjekt deutsch | Type | in scope | Tool / Method | Data Volume | WP1 flat | WP2 flat | WP3 | WP4 flat | WP20 | WP5 flat per system | WP6 | WP7 | WP8 | WP9 | WP14 | WP10 flat | WP11 flat | WP12 flat | WP13 flat | WP15 | WP16 flat | WP17 | WP18 | WP19 | Sum (Number of Days) |  | Comment | Sum
| Flat-rate number of days for some work packages |  |  |  | X |  |  | 5 | 5 | 5 | 2 | 15 | 5 |  |  | 0 |  | 0 |  | 2 | 1 | 4 |  | 5 |  |  |  | 49 | 49
1 | SD | Customer | Kunde | MD | X | MC / File | 12000 | [6 empty] | 1 | 2 |  | 2 |  | 0.5 |  |  |  | 1 |  | 0.25 | 0.5 | 0.5 |  | 7.75
2 | MM | Supplier | Lieferant | MD | X | MC / File | 250 | [6 empty] | 1 | 2 |  | 2 |  | 0.25 |  |  |  | 0.5 |  | 0.125 | 0.5 | 0.25 |  | 6.625
3 | LO | Product | Produkt | MD | X | MC / File | 32000 | [6 empty] | 1 | 2 |  | 3 |  | 0.5 |  |  |  | 1 |  | 0.5 | 1 | 0.25 |  | 9.25
[8 empty] | 5 | 5 | 5 | 2 | 15 | 5 | 3 | 6 | 0 | 7 | 0 | 1.25 | 2 | 1 | 4 | 2.5 | 5 | 0.875 | 2 | 1 | 72.625 | 72.625
Note on E3: Master = Stammdaten Transact. = Bewegungsdaten
Note on F3: Migrationsrelevant? X = JA leer = Nein
Note on Q3: Adopt SLT(MWB) object to customer needs
Note on R3: Adopt Rules for Extracting the data

## Effort Estimation (EN)
Company
[8 empty] | Data Analysis |  |  |  | Tools | Data Cleansing |  | Mapping | Implementation |  | Tests | [5 empty] | Productive Load |  |  | Data Validation |  | Column | Row
No. | Area | Migration Object english | Migrationsobjekt deutsch | Type | in scope | Tool / Method | Data Volume | WP1 Determine business objects to migrate flat | WP2 Identify source data systems flat | WP3 Historical data | WP4 Determine load sequence flat | WP20 Identify tools | WP5 Analyze data cleansing demand flat per system | WP6 Perform data cleansing | WP7 Create Mapping and Conversion rules | AP8 Create/adopt data migration procedures (incl. Test and documentation) | WP9 Create/adopt data extraction procedures (incl. Test and documentation) | WP14 Define and create test data load procedures flat | WP10 Provide test data flat | WP11 Plan test landscape flat | WP12 Implement test landscape flat | WP13 Create test plan for data migration flat | WP15 Test complete data migration | WP16 Create cut-over data migration plan flat | WP21 Extract / Provide data (optional) flat | WP17 Perform productive data migration | WP18 Define validation rules | WP19 Validate data | Sum (Number of Days) |  | Comment | Sum
| Flat-rate number of days for some work packages |  |  |  | X |  |  | 5 | 5 | 5 | 2 | 15 | 5 |  |  | 0 |  | 0 |  | 2 | 1 | 4 |  | 5 | 0.5 |  |  |  | 49.5 | 49.5
1 | SD | Customer | Kunde | MD | X | MC / File | 12000 | [6 empty] | 1 | 2 |  | 2 |  | 0.5 |  |  |  | 1 |  |  | 0.25 | 0.5 | 0.5 |  | 7.75
2 | MM | Supplier | Lieferant | MD | X | MC / File | 250 | [6 empty] | 1 | 2 |  | 2 |  | 0.25 |  |  |  | 0.5 |  |  | 0.125 | 0.5 | 0.25 |  | 6.625
3 | LO | Product | Produkt | MD | X | MC / File | 32000 | [6 empty] | 1 | 2 |  | 3 |  | 0.5 |  |  |  | 1 |  |  | 0.5 | 1 | 0.25 |  | 9.25
[8 empty] | 5 | 5 | 5 | 2 | 15 | 5 | 3 | 6 | 0 | 7 | 0 | 1.25 | 2 | 1 | 4 | 2.5 | 5 | 0.5 | 0.875 | 2 | 1 | 73.125 | 73.125
Note on E3: Master = Stammdaten Transact. = Bewegungsdaten
Note on F3: Migrationsrelevant? X = JA leer = Nein
Note on Q3: Adopt SLT(MWB) object to customer needs
Note on R3: Adopt Rules for Extracting the data

## Aufwandsschaetzung (DE)
Company
[8 empty] | Datenanalyse |  |  |  | Werkzeuge | Datenbereinigung |  | Mapping | Implementierung |  | Testen | [5 empty] | Produktives Laden |  |  | Datenvalidierung |  | Spalte | Zeile
Nr | Bereich | Migration Object english | Migrationsobjekt deutsch | Typ | relevant | Werkzeug / Methode | Anzahl der Datensätze | AP1 Datenmigrationsobjekte ermitteln pauschal | AP2 Quellsysteme identifizieren pauschal | AP3 Historiedaten | AP4 Ladesequenz ermitteln pauschal | AP20 Werkzeuge auswählen | AP5 Datenbereinigungsbedarf analysieren pauschal pro System | AP6 Datenbereinigung durchführen | AP7 Mapping und Konvertierungsregeln erstellen | AP8 Datenübernahme erstellen (inkl. F-Test und Doku) | AP9 Datenextraktprogramme erstellen (inkl. F-Test und Doku) | AP14 Testdaten Übernahmemethoden festlegen und erstellen | AP10 Testdaten bereitstellen (über alle Tests) | AP11 Testlandschaft planen pauschal | AP12 Testlandschaft einrichten pauschal | AP13 Testpläne für Datenübernahme erstellen pauschal | AP15 Gesamte Datenübernahme testen | AP16 Cut-Over-Migrationsplan erstellen pauschal | AP21 Daten extrahieren / bereitstellen (optional) pauschal | AP17 Daten produktiv laden | AP18 Prüfregeln erstellen | AP19 Daten validieren | Summen (Anzahl Tage) |  | Kommentar | Summe
| Pauschale Tage für einzelne Arbeitspakete |  |  |  | X |  |  | 5 | 5 | 5 | 2 | 15 | 5 |  |  | 0 |  | 0 |  | 2 | 1 | 4 |  | 5 | 0.5 |  |  |  | 49.5 | 49.5
1 | SD | Customer | Kunde | MD | X | MC / File | 12000 | [6 empty] | 1 | 2 |  | 2 |  | 0.5 |  |  |  | 1 |  |  | 0.25 | 0.5 | 0.5 |  | 7.75
2 | MM | Supplier | Lieferant | MD | X | MC / File | 250 | [6 empty] | 1 | 2 |  | 2 |  | 0.25 |  |  |  | 0.5 |  |  | 0.125 | 0.5 | 0.25 |  | 6.625
3 | LO | Product | Produkt | MD | X | MC / File | 32000 | [6 empty] | 1 | 2 |  | 3 |  | 0.5 |  |  |  | 1 |  |  | 0.5 | 1 | 0.25 |  | 9.25
[8 empty] | 5 | 5 | 5 | 2 | 15 | 5 | 3 | 6 | 0 | 7 | 0 | 1.25 | 2 | 1 | 4 | 2.5 | 5 | 0.5 | 0.875 | 2 | 1 | 73.125 | 73.125
Note on E3: Master = Stammdaten Transact. = Bewegungsdaten
Note on F3: Migrationsrelevant? X = JA leer = Nein
Note on Q3: Adopt SLT(MWB) object to customer needs
Note on R3: Adopt Rules for Extracting the data

## Keys
| Processing_Status | Prio
0% | 0% not started | High
25% | 25% dev in work | Med
50% | 50% conv in work | Low
75% | 75% test in work
100% | 100% completed
----------------
n.a.