## Sheet1
Home Renovation Budget
<Date>
<Ground floor renovation/second Story Addition/Full house renovation.
|  | Budget | Actual | Variance
Project Allowance
Finance - Loan Amount |  | 320000 | 320000 | 0
Cash |  | 6700 | 5800 | -900
<Other Income> |  | 0 | 0 | 0
<Other Income> |  | 0 | 0 | 0
Total Available Funds |  | 326700 | 325800 | -900
Project Expenses
Building Services Costs
Building designer/Architect |  | 8500 | 8500 | 0
Building Reports |  | 4500 | 4500 | 0
Building Insurance |  | 5500 | 5500 | 0
Council/Certifiers Fees |  | 2500 | 2500 | 0
Builder/Carpenter(labour+ materials) |  | 17400 | 18200 | -800
Electrician (labour + materials) |  | 660 | 660 | 0
Plumber (labour + materials) | Childcare | 1000 | 1000 | 0
Ducted Air Conditioning |  | 8000 | 8000 | 0
| Builders Preliminaries (12%) | 25000 | 25000 | 0
| <Other Building Services Costs> | 80000 | 80000 | 0
| <Other Building Services Costs> | 0 | 0 | 0
| <Other Building Services Costs> | 0 | 0 | 0
| <Other Building Services Costs> | 0 | 0 | 0
<Other Building Services Costs> |  | 0 | 0 | 0
Total Fixed Costs |  | 153060 | 153860 | -800
Building Materials Costs (by owner)
Bathroom - tiles |  | 300 | 360 | -60
Bathroom - bath |  | 360 | 295 | 65
Bathroom - tapware + fittings |  | 420 | 464 | -44
Bathroom - vanity |  | 650 | 650 | 0
Bathroom - Light/fan |  | 89 | 89 | 0
Bathroom - Shower screen |  | 810 | 810 | 0
Bathroom - Toilet |  | 310 | 290 | 20
| Kitchen - cabinetry | 4100 | 4100 | 0
| Kitchen - benchtop | 1500 | 1500 | 0
| Kitchen - sink + tapware | 350 | 325 | 25
| Kitchen - cooking Appliances | 1100 | 1100 | 0
| Kitchen - dishwasher | 600 | 600 | 0
| Kitchen - splashback (tile/glass) | 250 | 250 | 0
| Kitchen - Misc fittings/fixtures | 230 | 190 | 40
| Kitchen - Floor Tiles | 450 | 475 | -25
Miscellaneous - adhesives/Grout etc |  | 210 | 230 | -20
| <Other Miscellaneous costs> | 150000 | 140000 | 10000
| <Other Miscellaneous costs> | 0 | 0 | 0
| <Other Miscellaneous costs> | 0 | 0 | 0
| <Other Miscellaneous costs> | 0 | 0 | 0
| <Other Miscellaneous costs> | 0 | 0 | 0
| <Other Miscellaneous costs> | 0 | 0 | 0
<Other Miscellaneous costs> |  | 0 | 0 | 0
<Other Miscellaneous costs> |  | 0 | 0 | 0
<Other Miscellaneous costs> |  | 0 | 0 | 0
Total Building Materials Cost |  | 161729 | 151728 | 10001
Loan Repayment(s)/Rent - Monthly
Loan Repayment(s) - (month) |  | 300 | 300 | 0
Loan Repayment(s) - (month) |  | 300 | 300 | 0
Loan Repayment(s) - (month) | Clothing | 0 | 0 | 0
Rent - (month) |  | 1600 | 1600 | 0
Rent - (month) |  | 1600 | 1600 | 0
Rent - (month) |  | 0 | 0 | 0
Loan Repayment(s)/Rent |  | 3800 | 3800 | 0
Total Renovation Expenses |  | 318589 | 309388 | 9201
Total budget remaining |  | 8111 | 16412 | 8301