## Sheet1
Fall 2015 TheatreProduction Calendar v4
| Department - General |  | Sylvia | Into The Woods | Dr. Faustus | Other Experimental Theatre Events
|  |  | Exp Theatre | Exp Theatre | Don Powell
2015-08-24 | 1st Day of Classes |  | Sets into Shop (Aug 14th) |  | (First Design Meeting)
2015-08-25
2015-08-26 |  |  | PMtg | Design Mtg
2015-08-27 | General Auditions
2015-08-28 | General Auditions
2015-08-29
2015-08-30
2015-08-31
2015-09-01
2015-09-02 |  |  | PMtg | Design Mtg
2015-09-03
2015-09-04
2015-09-05 |  |  | Light Hang
2015-09-06 |  |  | Light Hang
2015-09-07 | Labor Day CAMPUS CLOSED |  |  | Prelim Scenic Drawings due
2015-09-08
2015-09-09 | HOLD POWELL HTM |  | PMtg | Design Mtg
2015-09-10 | HOLD POWELL HTM
2015-09-11
2015-09-12 |  |  | Light Focus
2015-09-13 |  |  | Light Focus
2015-09-14 |  |  | Load In | Finals Set Drawings toTD
2015-09-15 |  |  | Load In
2015-09-16 | HOLD POWELL HTM |  | PMtg Load In | Design Mtg
2015-09-17 | Film Festival |  | Load In
2015-09-18 | Film Festival |  | Levels
2015-09-19 |  |  | Tech 1
2015-09-20 |  |  | Tech 2
2015-09-21 |  |  | Dress1 | Sets into Shop
2015-09-22 |  |  | Dress2
2015-09-23 |  |  | Dress3/Run Photos | Design Mtg | Design Mtg
2015-09-24 |  |  | Dress4
2015-09-25 |  |  | Opening Night
2015-09-26 |  |  | Perf2
2015-09-27 |  |  | Perf3 (Mat)
2015-09-28 |  | Tour Meets 12-1
2015-09-29
2015-09-30 |  |  | Perf4 | Prod Mtg | Design Mtg (Set Prelims)
2015-10-01 |  |  | Perf5
2015-10-02 |  |  | Perf6
2015-10-03 |  |  | Perf7
2015-10-04 |  |  | Perf8 (Mat/Close)
2015-10-05
2015-10-06
2015-10-07 |  |  |  | Prod Mtg | Prod Mtg
2015-10-08
2015-10-09
2015-10-10 |  |  |  | Light Hang
2015-10-11 |  |  |  | Light Hang
2015-10-12 |  |  |  | Load in | Final Sets to Loren
2015-10-13 |  |  |  | Load in
2015-10-14 |  |  |  | Prod Mtg | Prod Mtg
2015-10-15 |  |  |  | Load in
2015-10-16 |  |  |  | Load in
2015-10-17 |  |  |  | Light Focus
2015-10-18 |  |  |  | Light Focus
2015-10-19 |  | Tour Meets 12-1 |  | Load In | Sets Into Shop
2015-10-20 |  |  |  | Load In
2015-10-21 |  |  |  | Load In | Prod Mtg
2015-10-22 |  |  |  | Load In
2015-10-23 |  |  |  | Levels
2015-10-24 |  |  |  | Tech 1
2015-10-25 |  |  |  | Tech 2
2015-10-26 |  | Tour Meets 12-1 |  | Dress1
2015-10-27 |  |  |  | Dress2
2015-10-28 |  |  | Sp #1 Design Meeting 12-1 | Dress3/Run Photos | Prod Mtg
2015-10-29 |  |  |  | Dress4
2015-10-30 |  |  |  | Opening Night
2015-10-31 |  |  |  | Perf2
2015-11-01 |  |  |  | Perf3 (Mat)
2015-11-02 |  | Tour Meets 12-1
2015-11-03
2015-11-04 |  |  | Sp #1 Design Meeting 12-1 | Perf 4 | Prod Mtg
2015-11-05 |  |  |  | Perf 5
2015-11-06 |  |  |  | Perf 6
2015-11-07 |  |  |  | Perf 7 | Light Hang
2015-11-08 |  |  |  | Perf 8 | Light Hang
2015-11-09 |  |  |  |  | Load In
2015-11-10 |  |  |  |  | Load In
2015-11-11 | Veterans Day No Classes |  | Sp #1 Design Meeting 12-1 |  | Load In
2015-11-12 |  |  |  |  | Load In
2015-11-13 |  |  |  |  | Load In
2015-11-14 |  |  |  |  | Light Focus
2015-11-15 |  |  |  |  | Light Focus
2015-11-16 |  |  |  |  | Load In
2015-11-17 |  |  |  |  | Load In
2015-11-18 |  |  | Sp #1 Design Meeting 12-1 |  | Load In
2015-11-19 |  |  |  |  | Load In
2015-11-20 |  |  |  |  | Levels
2015-11-21 |  |  |  |  | Tech
2015-11-22 |  |  |  |  | Tech
2015-11-23 |  |  | Spring Show #1 Prelims Done |  | Dress 1
2015-11-24 |  |  |  |  | Dress 2
2015-11-25 | NO CLASSES |  |  |  | OFF
2015-11-26 | Thanksgiving BreaK |  |  |  | OFF
2015-11-27 | Thanksgiving BreaK |  |  |  | OFF
2015-11-28 | Thanksgiving BreaK |  |  |  | OFF
2015-11-29 | Thanksgiving BreaK |  |  |  | OFF
2015-11-30 |  |  |  |  | Dress 3
2015-12-01 |  |  |  |  | Dress 4
2015-12-02 |  |  | Sp #1 Prod Meeting 12-1 |  | Open
2015-12-03 |  |  |  |  | P2
2015-12-04 |  |  |  |  | P3
2015-12-05 |  |  |  |  | P4
2015-12-06 |  |  |  |  | P5
2015-12-07 |  |  | Spring Show #1 Finals Done
2015-12-08
2015-12-09 |  |  | Sp #1 Prod Meeting 12-1
2015-12-10 | Last Day of Classes | Cirino Film Fest Powell
2015-12-11 | Finals Begin
2015-12-12 | OUTSIDE RENTAL POWELL
2015-12-13 | OUTSIDE RENTAL POWELL
2015-12-14 | Film Festival / Snd Final |  | Sets Into Shop Spring #1 Show
2015-12-15 | OUTSIDE RENTAL POWELL
2015-12-16 | OUTSIDE RENTAL POWELL
2015-12-17 | OUTSIDE RENTAL POWELL
2015-12-18 | OUTSIDE RENTAL POWELL
2015-12-19 | OUTSIDE RENTAL POWELL
2015-12-20 | OUTSIDE RENTAL POWELL
2015-12-21 | OUTSIDE RENTAL POWELL
2015-12-22 | OUTSIDE RENTAL POWELL
2015-12-23 | OUTSIDE RENTAL POWELL
2015-12-24 | OUTSIDE RENTAL POWELL
2015-12-25
2015-12-26
2015-12-27
2015-12-28
2015-12-29
2015-12-30
2015-12-31
2016-01-01
2016-01-02
2016-01-03
2016-01-04
2016-01-05
2016-01-06
2016-01-07
2016-01-08
2016-01-09
2016-01-10
2016-01-11
2016-01-12
2016-01-13
2016-01-14
2016-01-15
2016-01-16
2016-01-17
2016-01-18 | MLK Day
2016-01-19
2016-01-20 | First Day of Classes | SEE SPRING PRODUCTION CALENDAR | SEE SPRING PRODUCTION CALENDAR | SEE SPRING PRODUCTION CALENDAR | SEE SPRING PRODUCTION CALENDAR
2016-01-21
2016-01-22
2016-01-23
2016-01-24