## Sheet1
DUTIES
BEFORE REHEARSALS BEGIN | YES | DELEGATE | REFER TO | PAGE
EXAMPLE |  | ASM | Alice | 43
EXAMPLE | X |  | prior SM | 12
Determine duties
Read play, marking sound, light, shifts, special-effects and curtain cues
Create a scene/character breakdown
Make a diagram of the stage and set
Distribute rehearsal schedule
Distribute company rules
Make a promptbook
Create e-mail distribution lists for cast, crew and reports
DURING REHEARSALS
Set up rehearsal set pieces and props
Create a precurtain checklist
Spike set pieces
Call cues (lights, sound, special effects, curtain)
Choreograph/supervise scene changes
Track props
Take blocking notation
Prompt
Write and distribute rehearsal reports and daily schedules
DURING THE RUN | YES | DELEGATE | REFER TO | PAGE
Check for backstage hazards
Sweep/Mop stage before curtain and between acts if necessary
Give calls to actors
Collect and lock up valuables
Check in with house manager for okay to start
Check actors in place at top of each act
Call all necessary cues and watch for proper execution/result
Make notes of problems that occur
Supervise shifts
Make notes on line errors
Supervise backstage behavior of actors and crew
Write and distribute performance reports
AFTER FINAL PERFORMANCE
Make a strike plan
Supervise the strike
Work on strike crew
Write a critique of SM-related issues
Write letter of advice to SM of next production
Participate in post-production review
© Taylor & Francis 2021