## Slide 1: Sustainability Principles and Practice, 4th ed.
Project Management

## Slide 2: Project Management:
Planning, organizing, directing, and controlling resources
For a relatively short-term objective
To accomplish specific goals
Project management can be a professional discipline
Project managers can become certified

## Slide 3: Project management
But you don’t have to be certified to manage projects
National Institute of Standards and Technology (NIST)
“A project is a problem scheduled for solution.”
J. M. Juran, quality management leader

## Slide 4: Project: a one-time task
Defined objectives
Specific starting and ending point
Clearly defined scope of work
Budget
Team
It has:
9294202 Dreamstime

## Slide 5
Project manager delegates to a team.
Project manager does not do every task.
Delegation is a key skill.
With delegation, you are free to oversee details
You do not focus on individual elements, which are the responsibility of team members.

## Slide 6: Project manager
Planning
Scheduling
Activities
Facilitates:
Define project requirements
Define scope
Develop schedules
Develop budgets
Plan tasks
Lead project team
Monitor progress and adjust
Together with your team:

## Slide 7: 2 biggest causes of missed deadlines and cost overruns:
Project requirements
Scope
Not correctly defining . . .
“Projects often fail at the beginning, not the end.”
Lewis, James P. Project Planning, Scheduling, and Control, 3rd ed. New York: McGraw-Hill, 2000.

## Slide 8: Scope
Cost
Schedule
Performance
Deliverables
= boundaries of the project
Joebite, Dreamstime

## Slide 9: Scope creep
When project keeps growing beyond its original plan
Define project at the beginning
Monitor during the project
To prevent scope creep:
A great project plan
Scope creeping
Scope-creep crisis
Keep a record of all scope changes and their impact on budget or schedule.

## Slide 10: Three project constraints
QUALITY
TIME
COST
You can have any two; third has to vary
Any change to one affects other two
“Good, fast, or cheap—pick two.”

## Slide 11: Planning process
Goals
Strategies
Objectives
Tactics
Monitor and adapt
Goal: why you are here
If you define final result, you will know when project is done

## Slide 12: Planning process
Goals
Strategies
Objectives
Tactics
Monitor and adapt
Strategies: projects that will get you to your goal
Without a plan, you can’t manage the project
Plan tells you where you are supposed to be, and when

## Slide 13: Planning process
Goals
Strategies
Objectives
Tactics
Monitor and adapt
Specific
Measurable
Attainable
Relevant
Time-bound
SMART:
Objectives: How you will know whether your project is successful.

## Slide 14: Planning process
Goals
Strategies
Objectives
Tactics
Monitor and adapt
Tactics: actions; to-do list
It may look like 8-10 tasks.
There are probably 50 or 100 or more.

## Slide 15: Planning process
Goals
Strategies
Objectives
Tactics
Monitor and adapt
Set up a regular tracking system.
Monitor what was agreed.

## Slide 16: It’s about planning, planning, planning!
Including timelines
Whatever time you estimate, allow 2-10 times that much
Start with where you want to be, then work backwards to milestones.
List actions and sub-actions.
Check on the list every day.

## Slide 17: Project scheduling
Task
Responsibility (who)
Priority
Status
Date completed
Scheduling is time-consuming
Program revision
Lane Community College

## Slide 18: There are many ways to organize a plan
EPA grant proposal
Jennifer Hayward, Lane Community College

## Slide 19
There are many ways to organize a plan
This example is hard to understand.
A graphical method would be clearer.

## Slide 20
Some teams use spreadsheets.

## Slide 21: Some teams use sticky notes on a bulletin board. . .
or on a white board.
Kriscole, Dreamstime
Maximenko50, Dreamstime

## Slide 22
Graphical schedule
Shows each step on a separate line so time overlaps can be seen
Gantt chart
You don’t have to make a Gantt chart.
Many people find them useful.
US DOT - FHWA

## Slide 23
USGS Earthquake Hazards Program
Homemade schedule in Excel spreadsheet or
Scheduling software
You can use:

## Slide 24
You can use:
Homemade schedule in Excel spreadsheet
or
Office Timeline, a free PowerPoint add-on

## Slide 25
NASA
Homemade schedule in Excel spreadsheet
or
Microsoft Project – popular scheduling software
You can use:
NASA
Schedule
Schedule with milestones

## Slide 26
Hennebery Eddy Architects
Homemade schedule in Excel spreadsheet
or
Other scheduling software
You can use:

## Slide 27
Basecamp
Homemade schedule in Excel spreadsheet
or
Other scheduling software
You can use:
This is from Basecamp:

## Slide 28: Basecamp = collaboration software
Project management tool to help teams collaborate.
Has scheduling, to-do lists, message board, file sharing, and chat.
ASLA
AH Suite

## Slide 29: Scheduling
Divide into short tasks
  Assign people to each task
Determine task dependencies
  What comes before what?
Assign time to each task
  How long will it take?
Give each task a milestone (marker or measurement)
  Everyone knows when work is complete
- the implementation plan

## Slide 30
Milestones
Used since Roman times, milestones were numbered markers indicating position on a route or distance to a destination.
Route 22, Ohio
Route 126, Massachusetts
Library of Congress
Library of Congress

## Slide 31
Tracking
Use milestones in the schedule
Check: Are you where you should be?
EPA grant proposal
Jennifer Hayward, Lane Community College
Elnur, Dreamstime
A milestone is a marker or measurement

## Slide 32: Project management is about working with teams.
National Institute of Standards and Technology (NIST)
“When the best leader’s work is done the people say, ‘We did it ourselves.’”
--Lao Tzu