## Sheet1
Food Safety Co. (FSC) Project Management Gantt Chart
Tasks | Start Date | Duration (days) | End Date
Finalize Design Doc & Proj Management Contribution | 2011-09-13 | 6 | 2011-09-18
Final Design Doc sent to FSC for review | 2011-09-18 | 4 | 2011-09-21
Prototype development | 2011-09-26 | 14 | 2011-10-09
Analyze review comments & revise prototype | 2011-10-17 | 8 | 2011-10-24
Continued product development | 2011-10-10 | 15 | 2011-10-24
Usability testing of prototype at FSC | 2011-10-25 | 1 | 2011-10-05
Analyze usability results & revise design | 2011-10-26 | 20 | 2011-11-14
Conference Call via Centra with Client | 2011-11-15 | 1 | 2011-11-15
Final Product Development | 2011-10-26 | 34 | 2011-11-28
Final Presentation of Product to Client | 2011-11-29 | 1 | 2011-11-29
Analysis of Client feedback | 2011-12-02 | 5 | 2011-12-06