## Sheet1
Estimated construction costs includung everything but financing: | 1000000
Construcion timing | 14 months plus 6 months
Construction Rate | 5.5%
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Draw |  | 0.15 | 0.06 | 0.06 | 0.06 | 0.08 | 0.14 | 0.12 | 0.1 | 0.08 | 0.06 | 0.05 | 0.02 | 0.01 | 0.01
| cumulative | 0.15 | 0.21 | 0.27 | 0.33 | 0.41 | 0.55 | 0.67 | 0.77 | 0.85 | 0.91 | 0.96 | 0.98 | 0.99 | 1
| Net new draw | 150000 | 60000 | 60000 | 60000 | 80000 | 140000 | 120000 | 100000 | 80000 | 60000 | 50000 | 20000 | 10000 | 10000
| Cumulative | 150000 | 210000 | 270000 | 330000 | 410000 | 550000 | 670000 | 770000 | 850000 | 910000 | 960000 | 980000 | 990000 | 1000000
| Interest due | 687.5 | 690.651 | 968.8165 | 1248.2569 | 1528.9781 | 1902.6526 | 2553.0398 | 3114.7412 | 3587.3504 | 3970.4591 | 4263.657 | 4512.3655 | 4624.7138 | 4691.7438 | 4759.0809 | 4780.5847 | 4802.3972 | 4824.3082 | 4846.3192 | 4868.4306
| Additional reserve draw | 687.5 | 690.651 | 968.8165 | 1248.2569 | 1528.9781 | 1902.6526 | 2553.0398 | 3114.7412 | 3587.3504 | 3970.4591 | 4263.657 | 4512.3655 | 4624.7138 | 4691.7438 | 4759.0809 | 4780.5847 | 4802.3972 | 4824.3082 | 4846.3192 | 4868.4306
| Outstanding loan | 150687.5 | 211378.151 | 272346.9676 | 333595.2245 | 415124.2026 | 557026.8552 | 679579.895 | 782694.6361 | 866281.9866 | 930252.4457 | 984516.1027 | 1009028.4682 | 1023653.182 | 1038344.9257 | 1043036.6695 | 1047795.7504 | 1052576.3351 | 1057378.7323 | 1062203.0405 | 1067049.3597
| Month | 1: Explanation of sample of cost categories
| 1 | 1: Land costs or option fees, soft costs such as design and engineering, due diligence, soil testing, compaction, planning, marketing and government permit fees, consultant fees, BIM studies foer staging.
| 2 | 1: Equipment rental and materials planning, refining engineering and design, continuing to market space if necessary.
| 3 | 1: Digging equipment, foundation work, materials all enroute.
| 4 | 1: Concrete and steel work or concrete and framing
| 5 | 1: Framing or steel, walls poured or built.
| 6 | 1: Framing or steel, walls built.
| 7 | 1: Plumbing, electrical and ventilation work
| 8 | 1: Plumbing, electrical and ventilation work, floors and ceilings
| 9 | 1: Floors and celinings
| 10 | 1: Windows installed, safety equipment, walls finished, fixtures installed.
| 11 | 1: Painting, carpets, floors, elevators finishing if needed. Solar panels and roof equipment, water collection.
| 12 | 1: Landscaping and finishing for specific tenants.
| 13 | 1: Final TI costs, leasing fees, bonuses, government fees
| 14 | 1: Final TI and troubleshooting costs, commissioning studies and tweaking HVAC systems, marketing continuing.
| 15 | 1: Interest carry
| 16 | 1: Interest carry
| 17 | 1: Interest carry
| 18 | 1: Interest carry
| 19 | 1: Interest carry
| 20 | 1: Interest carry